Admin login (default):

- Email: admin@magayisa.local

- Password: Admin123!

If it does not work, it means environment overrides are active. In that case, use:

- MAGAYISA_ADMIN_EMAIL

- MAGAYISA_ADMIN_PASSWORD

Security note: change the default password immediately before wider testing.

Day-by-Day Implementation Plan (4 Weeks, 20 Working Days)

- Day 1

- Freeze scope for public launch: payment gateway choice, countries, payout policy, refund policy, support channels.

- Create launch tracker with owners and deadlines.

- Output: signed-off launch scope and risk register.

- Day 2

- Set up production infrastructure skeleton: production app host, managed Postgres, managed Redis, domain + HTTPS.

- Configure secrets storage for API keys and webhook secrets.

- Output: production-like environment online.

- Day 3

- Wire production runtime config and environment variables end-to-end.

- Verify health/readiness endpoints from external monitoring.

- Output: stable prod-like deployment with health probes passing.

- Day 4

- Implement real gateway checkout/session creation (sandbox mode first).

- Replace mock payment submission path with gateway redirect/hosted flow.

- Output: user can start real sandbox checkout.

- Day 5

- Implement webhook endpoint verification/signature checks.

- Add idempotency protection for duplicate webhook events.

- Output: paid events update booking/payment exactly once.

- Day 6

- Implement refund API integration with gateway sandbox.

- Ensure commission and payout reversal logic remains correct after real refunds.

- Output: refund flow works from app to gateway and back.

- Day 7

- Add payment failure and timeout handling UX.

- Add retry-safe behavior and clear user messaging.

- Output: resilient payment state machine for success/failure/pending.

- Day 8

- Security pass 1: remove/avoid raw card data handling, tighten input validation, secure headers, cookie checks.

- Add abuse controls for payment endpoints.

- Output: payment handling aligned to hosted/tokenized standards.

- Day 9

- Build reconciliation v1: daily totals from app vs gateway transaction export/API.

- Add mismatch report format for finance/admin review.

- Output: first daily reconciliation report.

- Day 10

- Add payout safeguards: maker-checker approval path, stricter audit entries, role review.

- Validate payout export + reconciliation together.

- Output: finance operations runbook draft complete.

- Day 11

- Monitoring setup: error tracking, uptime probes, alert routing to email/Slack/PagerDuty.

- Define severity matrix and on-call escalation.

- Output: actionable alerts with tested notifications.

- Day 12

- Backup and restore drill: Postgres backup restore test, app boot against restored snapshot.

- Test Redis outage behavior and graceful fallback.

- Output: disaster recovery evidence documented.

- Day 13

- Load test pass 1: login, browse trips, book, payment webhook bursts.

- Capture bottlenecks and tune app server/workers.

- Output: capacity baseline and tuning actions.

- Day 14

- Legal/ops readiness: privacy policy, terms, support contact flow, incident SOP.

- Add in-app links and footer references.

- Output: compliance + support minimum baseline complete.

- Day 15

- Internal UAT day: full script testing by team across passenger/driver/admin roles.

- Fix critical defects only.

- Output: UAT sign-off for external pilot.

- Day 16

- Pilot launch to 5–20 trusted users with very low real transaction amounts.

- Keep traffic cap enabled.

- Output: first live real-payment data.

- Day 17

- Analyze pilot telemetry: payment conversion, failed webhooks, refund behavior, support tickets.

- Patch top issues.

- Output: pilot stability improvements deployed.

- Day 18

- Reconciliation validation with real settlement data.

- Confirm payout numbers and audit log trail integrity.

- Output: finance sign-off for scaled beta.

- Day 19

- Pilot wave 2 (wider but still controlled).

- Re-run smoke tests, security checks, and rollback drill.

- Output: go/no-go package for public release decision.

- Day 20

- Final go-live review with checklist: infra, payments, security, monitoring, legal, support.

- If all green, remove/raise cap and open public access.

- Output: public launch approval and release announcement.

Definition of “Ready to Face Public” (must all be true)

- Real payment success/refund tested in live mode with verified webhooks.

- No raw card data stored by app.

- Postgres + Redis production services stable.

- Monitoring/alerts live and tested.

- Daily reconciliation matches gateway data.

- Backup/restore drill passed.

- Pilot users completed real transactions without critical incidents for multiple days.